## DSPT_Mapping
NHS Data Security and Protection Toolkit Mapping - Project SentinelCare - Westbridge Hospitals Trust
Standard # | Standard Name | Status | Key Evidence Finding | Linked Risk ID(s) | Improvement Plan Reference
1 | Personal Confidential Data | Partially Met | Inconsistent data classification and uncontrolled copies of patient reports |  | 061-data_classification
2 | Staff Responsibilities | Partially Met | Roles defined in stakeholder register but not all evidenced as trained on responsibilities |  | 006-stakeholders
3 | Training | Not Met | Low security awareness training completion, no Trust-wide tracking or reporting | CR-008 | 022-caf_assessment REC-004
4 | Managing Data Access | Not Met | Excessive user access privileges, inadequate access reviews, weak segregation of duties | CR-004 | 022-caf_assessment REC-002
5 | Process Reviews | Partially Met | Newly established risk register and asset register lack a full review cadence |  | 047-risk_methodology
6 | Responding to Incidents | Partially Met | Incident Response Plan exists; consistent testing cadence not evidenced |  | 08-Incident-Management
7 | Continuity Planning | Partially Met | Business Continuity and Disaster Recovery Plans exist; testing evidence inconsistent |  | 10-Business-Continuity
8 | Unsupported Systems | Not Met | 25 medical devices running unsupported operating systems, limited vendor patching options | CR-003 | 024-dsp_toolkit_review REC-001
9 | IT Protection | Partially Met | Security controls exist but not yet operated to a managed, continuously monitored standard | CR-009 | 022-caf_assessment REC-005
10 | Accountable Suppliers | Not Met | No central supplier security assessment process across 150+ suppliers | CR-006 | 024-dsp_toolkit_review REC-002