## CAF_Assessment
NCSC CAF Assessment - Project SentinelCare - Westbridge Hospitals Trust
Objective | Principle ID | Principle Name | Achievement Rating | Key Gap Summary | Linked Risk ID(s) | Evidence Reference
A - Managing Security Risk | A1 | Governance | Partially Achieved | No single governance forum reviewing control effectiveness Trust-wide (now chartered as CSGG in 05-Governance/051) |  | 021-current_state_assessment Â§4.1
A - Managing Security Risk | A2 | Risk Management | Partially Achieved | Risk register newly centralised; treatment actions predominantly Planned rather than embedded |  | risk_register Â§6
A - Managing Security Risk | A3 | Asset Management | Partially Achieved | Master asset register established but not yet subject to a managed review cycle |  | 022-master_assets_register.xlsx
A - Managing Security Risk | A4 | Supply Chain | Not Achieved | No central supplier security assurance process across 150+ suppliers | CR-006 | 025-supplier_register.xlsx
B - Protecting Against Cyber Attack | B1 | Service Protection Policies and Processes | Partially Achieved | Policies exist but applied inconsistently across departments |  | 021-current_state_assessment Â§4.1
B - Protecting Against Cyber Attack | B2 | Identity and Access Control | Not Achieved | Excessive user access privileges, inadequate access reviews, weak segregation of duties | CR-004 | 003-business-context Â§3.3
B - Protecting Against Cyber Attack | B3 | Data Security | Partially Achieved | Data classification framework now established, application not yet Trust-wide |  | 061-data_classification
B - Protecting Against Cyber Attack | B4 | System Security | Partially Achieved | Cloud identity single point of failure across Entra ID / M365 / Azure | CR-002 | 041-cloud_risk Â§4.2
B - Protecting Against Cyber Attack | B5 | Resilient Networks and Systems | Not Achieved | No recurring backup and disaster recovery test schedule with recorded outcomes | CR-011 | risk_register CR-011
B - Protecting Against Cyber Attack | B6 | Staff Awareness and Training | Not Achieved | Low security awareness training completion, no Trust-wide tracking or reporting | CR-008 | risk_register CR-008
C - Detecting Cyber Security Events | C1 | Security Monitoring | Not Achieved | Limited visibility of security events; SOC/MSSP capability not yet continuous or correlated | CR-009 | risk_register CR-009
C - Detecting Cyber Security Events | C2 | Proactive Security Event Discovery | Not Achieved | No proactive threat-hunting capability evidenced | CR-009 | 09-Security-Operations/064-threat_intelligence
D - Minimising the Impact | D1 | Response and Recovery Planning | Partially Achieved | Incident Response and Business Continuity Plans exist; consistent testing cadence not evidenced |  | 08-Incident-Management
D - Minimising the Impact | D2 | Lessons Learned | Partially Achieved | Ransomware tabletop exercise run; evidenced lessons-learned feedback loop not yet Trust-wide |  | 08-Incident-Management/Ransomware_Tabletop_Exercise