## Risk_Register
Cyber Risk Register - Project SentinelCare (WUHNFT)
Risk ID | Risk | Asset / Service | Threat | Vulnerability | Likelihood | Impact | Score | Rating | Risk Owner | Treatment Owner
CR-001 | Ransomware affecting clinical services | EPR, servers, clinical systems | Cyber criminals | Phishing, privilege escalation, insufficient segmentation | 5 | 5 | 25 | Critical | CDIO | CISO
CR-002 | Compromise of Microsoft 365 accounts | Microsoft 365 | Credential theft | Phishing and MFA fatigue attacks | 4 | 5 | 20 | Critical | CDIO | Identity Security Lead
CR-003 | Unsupported medical devices exploited | Medical devices | Malware exploitation | Legacy operating systems and limited patching | 4 | 5 | 20 | Critical | Clinical Engineering Manager | CISO
CR-004 | Excessive user access privileges | Patient systems | Insider misuse / account compromise | Poor access reviews | 4 | 4 | 16 | High | Information Asset Owners | IAM Manager
CR-005 | Patient data exposure | EPR and reporting platforms | Data leakage | Poor classification and uncontrolled copies | 4 | 5 | 20 | Critical | Data Protection Officer | Information Governance Team
CR-006 | Third-party supplier compromise | Supplier connections | Supply chain attack | Limited supplier assurance process | 4 | 5 | 20 | Critical | Procurement Director | Supplier Security Manager
CR-007 | Incomplete asset inventory | IT infrastructure | Unknown vulnerabilities | Inaccurate asset ownership records | 4 | 4 | 16 | High | Infrastructure Manager | IT Asset Manager
CR-008 | Security awareness failure | Workforce | Phishing attacks | Low training completion | 4 | 4 | 16 | High | HR Director | Security Awareness Lead
CR-009 | Insufficient security monitoring | Security operations | Undetected attack activity | Limited security metrics and monitoring capability | 3 | 5 | 15 | High | CISO | SOC Manager
CR-010 | Clinical service disruption | Critical healthcare services | System outage | Weak resilience and recovery testing | 3 | 5 | 15 | High | Chief Operating Officer | Business Continuity Manager
CR-011 | Data loss due to inadequate backup protection | Critical systems | Ransomware/destructive attack | Backup testing and resilience gaps | 3 | 5 | 15 | High | Infrastructure Manager | Backup Service Owner
CR-012 | Cloud security misconfiguration | Azure services | Unauthorised access | Incorrect configuration and insufficient governance | 3 | 5 | 15 | High | Cloud Service Owner | Cloud Security Engineer