## CAPA_Tracker
Corrective and Preventive Action Tracker - WHT Internal Audit
CAPA ID | Finding Ref | Description | Root Cause | Corrective Action | Priority | Owner | Target Date | Status | Linked Risk/REC
CAPA-001 | AUD-001 | Guest Wi-Fi controller default administrative credentials (VUL-007, CVSS 9.8), no compensating control, no linked risk | No forcing function for Critical findings outside vendor-constrained assets | Change default credentials immediately; link finding to a tracked risk ID; extend register escalation logic to cover all Critical findings | Critical | Infrastructure Manager | 2026-08-06 | Open | -
CAPA-002 | AUD-002 | No offline/immutable backup copy; no recurring backup/disaster recovery test performed | CR-011 treatment action (offline/immutable backup) still Planned, not started | Implement offline/immutable backup copy; establish recurring backup/DR test schedule with recorded outcomes | High | Backup Service Owner | 2026-12-31 | Open | CR-011; CAF REC-003
CAPA-003 | AUD-003 | Role-based access control and recurring access review cycle not implemented | CR-004 treatment action still Planned, not started | Implement RBAC across in-scope systems; establish recurring access review cycle | High | IAM Manager | 2027-03-31 | Open | CR-004; CAF REC-002
CAPA-004 | AUD-004 | Security monitoring dependent on single MSSP relationship; no continuous correlated detection | CR-009 treatment action (expand SOC/MSSP coverage) still Planned | Expand SOC/MSSP monitoring coverage; define fallback arrangement for MSSP disruption | High | CISO | 2027-03-31 | Open | CR-009; CAF REC-005
CAPA-005 | AUD-005 | VUL-002 (unattributed network switches) remains unresolved due to incomplete asset ownership records | CR-007 (incomplete asset inventory) not yet closed | Complete asset ownership verification for affected network devices; cross-reference CR-007 to dependent vulnerability register entries | Medium | Infrastructure Manager | 2026-09-30 | Open | CR-007
CAPA-006 | AUD-006 | No chartered Internal Audit function or documented Three Lines Model | Governance documentation has defined the Second Line (CSGG) but not Third Line independence and mandate | Charter a formal Internal Audit function or co-sourced provider arrangement; document the Three Lines Model in role definitions | Medium | Audit and Risk Committee | 2026-12-31 | Open | -
CAPA-007 | AUD-007 | Security awareness training not yet mandatory or completion-tracked | CR-008 treatment action still Planned, not started | Implement mandatory tracked training with completion reporting to CSGG | Medium | Security Awareness Lead | 2027-03-31 | Open | CR-008; CAF REC-004
CAPA-008 | AUD-008 | DSPT overall assessed outcome is Standards Not Met; no formal improvement plan yet agreed | DSPT REC-005 (agree formal improvement plan with NHS England/ICB) remains open | Agree and submit formal DSPT improvement plan with NHS England/ICB | High | CISO | 2026-09-30 | Open | DSPT REC-005
CAPA-009 | AUD-009 | Recommendation IDs (REC-XXX) reused with different meanings across 25+ documents; no consolidated cross-document tracker existed before this audit | No single owner accountable for recommendation-tracking consistency across the programme | Maintain this CAPA tracker as the single consolidated tracker for all open recommendations; review quarterly alongside the CSGG report | Low | Head of Internal Audit | Ongoing | In Progress | This document